## 1. Budget Analysis (hidden)
Applied filters: | Workspace ID IN (21315145)
Date (Workspace Start Date) BETWEEN THIS-125 AND THIS-2
Workspace ID | Workstream/Work Group | Resource Name | Title | Bill Rate | Fees Actual To Date | Budgeted | Fees Remaining | Actual Hours To Date | Budgeted Hours | Hours Remaining
Project Governance
Wellforce SOW002 | Project Governance | Greg Kitzerow | Project Manager | 181 | 36562 | 130320 |  | 202 | 720h
|  | Lee Wallace | Engagement Manager | 189 | 12474 | 13608 |  | 67 | 72h
Project Governance Totals:
| Finance Workstream | Dana Mercure | Finance Principal | 173 | 23960.5 | 209330 |  | 138.5 | 1,210h
|  | Carol McGuire | Finance Principal | 173 | 1989.5 | 209330 |  | 11.5 | 1,210h
Finance Workstream Rollup
| Human Capital Workstream | Bridget Lyons | HCM+Payroll Principal | 173 | 36503 | 155700 |  | 211 | 900h
HCM Workstream Rollup
| Supply Chain Workstream | Stephanie Pacienza | Supply Chain Principal | 173 | 45672 | 173000 |  | 264 | 1,000h
|  | Yusuf Guvenc | Supply Chain Principal | 173 | 519 | 173000 |  | 3 | 1,000h
SCM Workstream Rollup
| Technical Workstream | Joe Foster | Technical Project Manager | 181 | 18281 | 26064 |  | 101 | 144h
|  | Andrew Woodward | Technical Architect | 173 | 692 | 67124 |  | 4 | 388h
|  | Michael Smith | Technical Architect | 189 | 189 | 67124 |  | 1 | 388h
|  | David Tashima | Interfaces | 173 | 173 | 281940 |  | 1 | 2,880h
Technical Workstream Rollup

## B v A
<Company Logo> | Project Budgetary Analytics Tool (Budget vs. Actuals) | [9 empty] | <CLIENT | LOGO>
Report Date: | 2020-01-01
Project Resource Name | Project Team Role | Hourly Rate | Original Budget | Actual To Date | Estimate to Complete | Estimate at Completion | Variance | % Budget Used to Date (Burn Rate) | Actual Hours Billed To Date | Budgeted Hours | Hours Remaining | % Hours Used to Date (Burn Rate)
Project Governance Team
Resource | Project Manager | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Resource | Engagement Manager | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #VALUE! | #VALUE!
Project Governance Totals: |  | N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 |  | #VALUE! | #VALUE!
Finance Mgmt. Team
Resource | Finance Principal | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Resource | Finance Sr Consultant | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Resource | Finance Line Consultant | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Finance Workstream Totals: |  | N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Supply Chain Mgmt. Team
Resource | Supply Chain Principal | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0%
Resource | Supply Chain Consultant | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
SCM Workstream Totals: |  | N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0%
Human Capital Mgmt. Team
Resource | HCM+Payroll Principal | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0%
HCM Workstream Totals: |  | N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0%
Technical Team
Resource | Tech Project Manager | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Resource | Tech Architect | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Resource | Tech Architect | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Resource | Interface Developer | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Technical Workstream Totals: |  | N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0%
TOTAL: |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | #VALUE!
PROJECT COST TRACKING STATUS IS GREEN: The total of project invoices to date and average expenditures across all workstreams is at or below the expected burn rate |  |  |  |  | PROJECT HOURLY TASK BURN RATE IS GREEN: The average number of hours used across all workstreams is at or below the expected burn rate | [6 empty] | Overall Project Status
PROJECT COST TRACKING |  |  |  |  | PROJECT TIME TRACKING | [6 empty] | For a complete explanation of how this tool calculates the TIME and EXPENSE burn rates, please see the ASSUMPTIONS tab
Project Workstreams | Percent Expected Burn Rate (Budget) | Percent Invoiced to Date (Actuals) |  | Variance to Plan | Project Workstreams |  |  | Percent Expected Burn Rate (Hours) | Percent Hours Used to Date (Actuals) | Variance to Plan | Work Plan Task Utilization Status
Project Governance | 37% | #DIV/0! |  | #DIV/0! | PM |  |  | 37% | #VALUE! | #VALUE!
Finance Workstream | 37% | #DIV/0! |  | #DIV/0! | FIN |  |  | 37% | #DIV/0! | #DIV/0!
Supply Chain Workstream | 37% | #DIV/0! |  | #DIV/0! | SCM |  |  | 37% | 0% | 37%
Human Capital Workstream | 37% | #DIV/0! |  | #DIV/0! | HCM |  |  | 37% | 0% | 37%
Technical Workstream | 37% | #DIV/0! |  | #DIV/0! | TECH |  |  | 37% | 0% | 37%

## Assumptions
Name of Project [XXX-000] (Project Number: SOW, Contract Number or Other Referenceable Entry) Project Assumptions: Rate: $000/hr Budgeted Hours: 0 Project Budget: $0 Engagement Start Date: <Start Date> Scheduled End Date: <Scheduled End Date> Number of Weeks: 00
Project Invoices/Hrs Billed Proj. Week Rem. Hrs
00/00 - 00/00 00 hrs 01 000.0
00/00 - 00/00 00 hrs 02 000.0
00/00 - 00/00 00 hrs 03 000.0
00/00 - 00/00 00 hrs 04 000.0
00/00 - 00/00 00 hrs 05 000.0
00/00 - 00/00 00 hrs 06 000.0
00/00 - 00/00 00 hrs 07 000.0
00/00 - 00/00 00 hrs 08 000.0
00/00 - 00/00 00 hrs 09 000.0
00/00 - 00/00 00 hrs 10 000.0
00/00 - 00/00 00 hrs 11 000.0
00/00 - 00/00 00 hrs 12 000.0
00/00 - 00/00 00 hrs 13 000.0
00/00 - 00/00 00 hrs 14 000.0
Final Project Total: 000.0 hours billed
0.0 hours remaining

## Sheet2 (hidden)
Effective Project Dates | 2018-08-15 | thru | 2019-04-30
Number of Months | 8.5
Number of Weeks | 34
Number of Days | 170
As of October 15, 2018 | 43 days used |  | 127 days remaining
Progress of Project to Date: |  | 25.29%
As of Oct 15th Project is in its 9th week |  | 25.29%
As of Oct 15th 43 days have been used |  | 25.29%